## Sheet1
Risk ID | Risk Title | Category | Description | Likelihood (1–5) | Impact (1–5) | Risk Score | Heat Level | Controls / Mitigations | Residual Risk | Owner | Status
R-001 | Data Breach via Phishing | Cybersecurity | Attackers may compromise accounts through phishing | 3 | 5 | 15 | High | MFA; phishing training; email filtering | Medium | CISO | Active
R-002 | Third-Party Vendor Failure | Operational | Vendor outage disrupts service delivery | 3 | 3 | 9 | Medium | SLA monitoring; redundancy; vendor reviews | Low | Vendor Manager | Active
R-003 | Regulatory Non-Compliance | Compliance | Failure to meet GDPR requirements | 2 | 5 | 10 | Medium | DPIAs; audits; retention policies | Medium | Compliance Lead | Active
R-004 | Insider Threat | Security | Malicious or negligent employee causes data loss | 2 | 5 | 10 | Medium | Access controls; monitoring; least privilege | Medium | SecOps | Monitoring
R-005 | Cloud Misconfiguration | Technology | Incorrect cloud settings expose data | 3 | 5 | 15 | High | Config scanning; IaC; reviews | Medium | Cloud Architect | Active
R-006 | Business Continuity Failure | Resilience | Disaster event halts operations | 2 | 5 | 10 | Medium | BCP/DR plans; backups; failover testing | Medium | COO | Planned
R-007 | Financial Fraud | Financial | Fraudulent transactions or manipulation | 2 | 5 | 10 | Medium | Segregation of duties; audits | Low | CFO | Active
R-008 | Reputational Damage | Strategic | Negative publicity impacts trust | 3 | 5 | 15 | High | PR strategy; quality controls | Medium | CEO | Monitoring
R-009 | Intellectual Property Theft | Legal | Theft of proprietary information | 2 | 5 | 10 | Medium | NDAs; DLP tools; access restrictions | Medium | Legal Counsel | Active
R-010 | System Outage | Technology | Critical system downtime | 3 | 3 | 9 | Medium | Monitoring; redundancy; patching | Low | IT Ops | Active